## Sheet1
Task | Start Date | End Date | Duration
Project Planning and PDD Submission | 2025-01-20 | 2025-02-02 | 13
Review PDD and Resubmit if Needed | 2025-02-03 | 2025-02-09 | 6
Context Review and Initial Research | 2025-02-05 | 2025-02-14 | 9
Start Data Collection | 2025-02-10 | 2025-02-16 | 6
Create Basic UI | 2025-02-10 | 2025-02-16 | 6
Model Development and Follower Analysis | 2025-02-17 | 2025-03-07 | 18
Continue Refining UI | 2025-02-17 | 2025-03-07 | 18
Submit Final Ethics Material for Approval | 2025-03-10 | 2025-03-15 | 5
User Testing and Feedback | 2025-03-20 | 2025-04-11 | 22
Draft Report | 2025-03-15 | 2025-04-11 | 27
Continue Working on UI and Tool | 2025-03-15 | 2025-04-11 | 27
Show Supervisor and Receive Feedback | 2025-04-07 | 2025-04-11 | 4
Finish Tool and Prepare Product Package | 2025-04-13 | 2025-04-22 | 9
Finish Project Report and Submit | 2025-04-22 | 2025-04-29 | 7